## Slide 1: Review to Address
Technical procedures
  Construction
  Testing
Facility
Workforce and Schedule

## Slide 2: iTPC Project Overview
Flemming Videbæk
BNL
Notes: Main point to introduce the overall iTPC project over and above the MWPC production

## Slide 3: Overview
What is the project
What are the production plans
Schedule & Progress
Performance goals

## Slide 4
The STAR Upgrades and BES Phase II
iTPC Upgrade:
Rebuilds the inner sectors of the TPC
Continuous Coverage
Improves dE/dx
Extends h coverage from 1.0 to 1.5
Lowers pT cut-in from 125 MeV/c to 60 MeV/c
EPD Upgrade:
Allows a better and independent reaction plane measurement critical to BES physics
Improves trigger
Reduces background
EndCap TOF Upgrade:
PID at h = 0.9 to 1.5
Provided by CBM-FAIR
Major improvements for BES-II
Endcap TOF

## Slide 5: Current TPC
Notes: Has worked well for many years (1999) and produced extraordinary results.

## Slide 7: Upgrade key elements
Replacement of Inner Sectors (24)
  Increase #padrows from 13 to 40.
  Complete geometrical coverage
    Mechanical Sector (Strongbacks)
    Joining of padplanes with strongbacks
    Assembly of MWPC on strongbacks
This will improve
  eta coverage from 1.0 to 1.5
  Pt coverage from 0.20 -> 0.06 GeV/c
  dE/dx
Notes: Add some drawings

## Slide 8: Strong back
Strongback, commercial fabrication
Padplane , same # even/odd per connector
Notes: Implies one could reuse the old electronics for ½ padrows (20 over 13)

## Slide 9: Close-up cross section

## Slide 10: Existing MWPC
Notes: Notice the tight tolerances

## Slide 11: Example of CAD model of assembly process

## Slide 12: Pad-plane assembly
At this point all strong backs have been produced
The assembly of the pad-plane with the strongback will be done at LBNL
Significant work has gone into the initial process of aligning the different side mount to get proper distances
Many details in talk at TCSM review (Jim Thomas)
Work at LBNL is gearing up toward with detailed tooling design
Assembly work will be on-going throughout Jan-May
As this proceeds the MWPC production must be going strong (Fb-March 2017)

## Slide 13: Electronics
Electronics to handle increase of channels
  Similar FEE layout and foot print as for existing DAQ1000 cards
  Double #channels per FEE
    55 FEE per inner sector
  RDO modules
    3 RDO per sector
  DAQ PCs

## Slide 14: Electronics development
Prototype FEE and RDO.
-Install 2 FEE and RDO for upcoming run (next week) in an inner padrow. Important development step.
A year from now plan on enough electronics for a full inner sector.

## Slide 15: Installation
Installation in STAR
  Replace existing inner 24 sector with new
    Involves removing all electronics service, remove and insert new, reinstall services
  Mount new electronics
  This by it self is a delicate task. Ensure no dirt gets into TPC, and the sectors work ahead of installation
Commissioning

## Slide 16: Work distribution
Strongback (BNL)
Pad plane joining (LBNL – subcontract)
MWPC assembly and testing (SDU,USTC,)
Sector testing at RHIC (BNL+..)
Electronics (BNL)
Installation (BNL)
Commissioning and code (BNL,SDU,USTC, other institutions)

## Slide 17: Timeline
Proposal several years ago (Late 2011)
Internal STAR review Feb 5, 2015
Proposal submitted and Physics Review by PAC in June 2015
Follow-up discussion with ALD sufficient to proceed to technical review
TDR completed and submitted to ALD November
Risk assessment requested by ALD for TPC and iTPC submitted early December
Directors review January; approval to proceed granted in February due to need to acquire long lead items (strongback, padplanes, setting contact with LBNL) ahead of the this review.
TCSM DOE review in September

## Slide 18: Schedule Background
The Start and length of run-18 directly impacts the start of run-19 since about 10 month is needed to roll in/out, replace of inner sectors, electronics, and commisioning
A run-18 installation of a new inner sector will gain experience with methods and installation time required
Currently run-18 is scheduled for 13 cryo weeks, and is coupled to CA-D LEReC R&D progress

## Slide 19: Some key milestones
Install one new sector in fall of 2017
All sectors at BNL by summer 2018
Tested and installed by Oct 2018
Commissioning Oct-Feb 2019

## Slide 20: Summary Schedule
Current schedule has STAR ready for data taking March 2019, with ~1.5 month of commissioning. Single sector tested in run-18 Key goal of project is to have upgrade complete for Run-19.
Critical path goes through electronics path a) (SAMPA chip )
b) sector production installation, and testing & commissioning
Calendar Year |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Mechanical |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
padplane |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Strongback production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Padplane Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assemble MWPC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sector Installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Electronics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RDO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SAMPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FEE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Electronics installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Roll-in and commisioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Insertion Tool |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Notes: Missing electronics -- as of summer

## Slide 21: Progress
Completed strongback design
Initiated and completed strongback production
Completed padplane design
Completed padplane pre-production
  Had production issues at the PCB factory, that had previous made a successful prototype pad plane, and procurement delays
First 14 padplanes will be delivered 12/6/16

## Slide 22: Progress
Worked with LBL junior engineer to provide assembly instruction for the padplane joining
High precision work to get proper distanced from wire mounts to padplane.
Prototyping and experience gained at SDU
Prototype FEE and RDO produced and works

## Slide 23: Performance Criteria
The resolution of the dE/dx is a critical parameter for the performance of the TPC The upgraded TPC with the inner sectors will provide part of the total dE/dx signal. For || > 1 the inner sectors are the dominating contributor to the dE/dx and considerable better than the current TPC. This can be measured with beam and be demonstrated after several months of calibration work.
A critical test that will be done during the construction is the measure the response of 55Fe source on the wires

## Slide 24: Improved performance
Increase rapidity coverage η ~1 to ~1.5
Increased efficiency for η >1 both in pT and particle specie |η| < 1.5
Improved dE/dx
η
Rapidity y
pT
dE/dx

## Slide 25: Summary
iTPC is an ambitious project on a relatively short time-scale to completion.
All the necessary pieces are coming together, and we are entering the production phase.
The installation and commissioning must be carefully executed not to harm the ongoing and future STAR physics program